## Activities
Activity ID | Activity Name | Activity Status | BL Project Finish | Finish | Units % Complete | Variance - BL Project Finish Date | Budgeted Labor Units
A-100 |  |  | 2026-02-16 | 2026-02-23 | 85 | -1 | 1000
A-110 |  |  | 2026-02-02 | 2026-02-09 | 82 | -1 | 600
A-111 | Mobilize crew | Completed | 2026-01-19 | 2026-01-26 | 95 | 1 | 300
A-112 | Temporary works | In Progress | 2026-01-26 | 2026-02-02 | 72 | 2 | 300
A-120 | Foundations | Not Started | 2026-02-02 | 2026-02-09 | 61 | 3 | 400

## Ressource Assign. Budgeted
Activity ID | Start | Finish | Budgeted Units | Spreadsheet Field | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19
A-100 | 2025-11-24 | 2026-02-23 | 1000 | Cum Budgeted Units | 50 | 120 | 220 | 350 | 500 | 650 | 800 | 900 | 1000
A-110 | 2025-11-24 | 2026-02-23 | 600 | Cum Budgeted Units | 30 | 72 | 132 | 210 | 300 | 390 | 480 | 540 | 600
A-111 | 2025-11-24 | 2026-02-23 | 300 | Cum Budgeted Units | 15 | 36 | 66 | 105 | 150 | 195 | 240 | 270 | 300
A-112 | 2025-11-24 | 2026-02-23 | 300 | Cum Budgeted Units | 15 | 36 | 66 | 105 | 150 | 195 | 240 | 270 | 300
A-120 | 2025-11-24 | 2026-02-23 | 400 | Cum Budgeted Units | 20 | 48 | 88 | 140 | 200 | 260 | 320 | 360 | 400

## Ressource Assign. Actual
Activity ID | Start | Finish | Budgeted Units | Spreadsheet Field | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19
A-100 | 2025-11-24 | 2026-02-23 | 1000 | Cum Actual Units | 30 | 90 | 170 | 280 | 400 | 520 | 650 | 780 | 900
A-110 | 2025-11-24 | 2026-02-23 | 600 | Cum Actual Units | 18 | 54 | 102 | 168 | 240 | 312 | 390 | 468 | 540
A-111 | 2025-11-24 | 2026-02-23 | 300 | Cum Actual Units | 9 | 27 | 51 | 84 | 120 | 156 | 195 | 234 | 270
A-112 | 2025-11-24 | 2026-02-23 | 300 | Cum Actual Units | 9 | 27 | 51 | 84 | 120 | 156 | 195 | 234 | 270
A-120 | 2025-11-24 | 2026-02-23 | 400 | Cum Actual Units | 12 | 36 | 68 | 112 | 160 | 208 | 260 | 312 | 360

## Ressource Assign. Remaining
Activity ID | Start | Finish | Budgeted Units | Spreadsheet Field | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19
A-100 | 2025-11-24 | 2026-02-23 | 1000 | Cum Remaining Early Units | 50 | 120 | 220 | 340 | 460 | 600 | 750 | 880 | 980
A-110 | 2025-11-24 | 2026-02-23 | 600 | Cum Remaining Early Units | 30 | 72 | 132 | 204 | 276 | 360 | 450 | 528 | 588
A-111 | 2025-11-24 | 2026-02-23 | 300 | Cum Remaining Early Units | 15 | 36 | 66 | 102 | 138 | 180 | 225 | 264 | 294
A-112 | 2025-11-24 | 2026-02-23 | 300 | Cum Remaining Early Units | 15 | 36 | 66 | 102 | 138 | 180 | 225 | 264 | 294
A-120 | 2025-11-24 | 2026-02-23 | 400 | Cum Remaining Early Units | 20 | 48 | 88 | 136 | 184 | 240 | 300 | 352 | 392

## README
Chronoplan Excel template
Activities sheet:
- Include Budgeted Labor Units (last column) for all activities.
- Keep one header row with the required columns.
- Indent Activity ID with spaces to represent the hierarchy.
- Activity Name is required only for leaf activities.
- Activity Status must be filled when Activity Name is filled.
- Dates can be Excel dates or YYYY-MM-DD.
Resource Assignments sheets:
- Keep one table per sheet with the same Activity IDs.
- Keep the same indentation in Activity ID for all tables.
- Spreadsheet Field must be one of:
Cum Budgeted Units, Cum Actual Units, Cum Remaining Early Units.
- Weekly columns are week start dates (Monday).